## WBS
N | Feature | Task | Description | DoD | Note | Risks | Estimation in hours | User stories
| Book management | Create Book base class | Implementation of book class with all attributes as title, author, category and availability status | Docstring Private attributes
|  | Implement borrow and return book | To be implemented functions controlling borrowing and returning books | borrow_book() method change availability status to not available return_book() method change availability status to available
|  | Create Special book class | To be created special book class | TODO
|  | Test book class | Implement set of test to cover the entire class | Test create a book with valid / invalid data Test borrow and return
| User management | Create User class | Implement a User class with attributes: Name, borrowed book | Docstring Private attributes
|  | Implement user methods | To be implemented functions to see how many books are borrowed, do add and remove from borrowed list | get_borrowed_books() return borrowed books add_borrowed_books() adding to borrowed books remove_borrowed_books() remove from borrrowed books limit_amount_borrowed_books() to limit how many books can be borrowed
|  | Test book class | Implement set of test to cover the entire class | To be tested all method and edge cases
| Library management | Create library classs | Implement a library class with attributes: all_books and all_users | Docstring Private attributes
|  | Implement library methods | Implement functions to add new book, to register a new user, to get available books, to return all books, to return all registerd books | add_book() adding book in library register_user() adding new user get_available_books() returns list of not borrowed books get_all_users() retuns list of all users get_all_books() returns list of all bookslibrary has
|  | Test book class | Implement set of test to cover the entire class | To be tested all method and edge cases
| Structure setup | Create project structure | To create folders and additional files required for the project | To have structure with all folders as src/test/coverаge To have setup for venv

## Questions
Question | Answer